## Sheet1
STREET STYLE STORE
Identified By: Arjun R Reported To: Environment Details: MacOS , Safari Date: 07-08-2023 Version No:
Bug ID | Test ID | Bug Description | Steps to Reproduce | Severity | Priority | Screenshot | Status
DEF_SSS_01 |  | the password field has no requirment of characters or numbers | 1.open registration page 2.enter mobile number 3.enter otp 4enter password | major | high | https://drive.google.com/file/d/1_VeRkjJyLaai 0KDA5NG2JsZWrwwZsH8w/view?usp=sharing | new
DEF_SSS_02 |  | no tool tip of the icons | 1.open the page 2.put the cursor on the icons 3.type full name | minor | low | https://drive.google.com/file/d/1saQwjnRiEX7aw qJ9aP9G0Le_tmS-MXzZ/view?usp=sharing | new
DEF_SSS_03 |  | show password icon is not working | 1.open registration page 2.enter mobile number 3.enter otp 4enter password | major | high | https://drive.google.com/file/d/1_VeRkjJyLaa i0KDA5NG2JsZWrwwZsH8w/view?usp=sharing | new
DEF_SSS_04 |  | search results are not relevent | 1.open the website 2.click on the search bar 3.type the required item | minor | low | https://drive.google.com/file/d/1h-kmIXHq8gV9-tTsbZCnwcKGg8wGqNgI/view?usp=sharing | new
DEF_SSS_05 |  | drop down menu is in the otp section | 1.open registration page 2.enter mobile number 3.enter otp 4enter password | major | high | https://drive.google.com/file/d/1WVGsO- 42sTX6oAh_TGgozhIvg-Cjyg6u/view?usp=sharing | new
DEF_SSS_06 |  | alignment was not much proper | 1.open the website 2.make fullscreen | minor | high | https://drive.google.com/file/d/1wbLxLhqWIZ2 E7nHtAbSOz7FIMBdUlMKd/view?usp=sharing | new
DEF_SSS_07 |  | buynow option is not present in the product view page | 1.open the website 2.select any item | minor | low | https://drive.google.com/file/d/1W_yiRFMe yCEGpYxuvTUyBe6uODeCwBeo/view?usp=sharing | new
DEF_SSS_08 |  | there is no reviews of the customers in the product view page | 1.open the website 2.select any item | minor | low | https://drive.google.com/file/d/1W_yiRFMeyC EGpYxuvTUyBe6uODeCwBeo/view?usp=sharing | new
DEF_SSS_09 |  | address was saved 2 times when we add a new address | 1.open the website 2.click on my account icon 3.select address option 4.enter new address | minor | low | https://drive.google.com/file/d/1vxE7pGDFMB MsKgvrn6YFcyRLB0qo5vpW/view?usp=sharing | new
DEF_SSS_10 |  | pincode field is more than 6 numbers | 1.open the website 2.select any item 3.click on the pincode field 4.enter pin code | minor | high | https://drive.google.com/file/d/1grlboaT3 typAk7PWS2vWTkiIwgj-pKpj/view?usp=sharing | new